## Sheet1
Risk Register
| Risk ID | Category | Owner | Description (including mitigation/solution) | Status | Probability | Impact | Risk Exposure
| R5 | Technical Risk | Security Engineer / Developer | Unauthorized access or data breach of student results. Mitigation: Implement authentication, encryption, role-based access control, and security testing. | identified | 8 | 7 | 56
| R1 | Business Risk | Project Manager / Management | Budget overrun or insufficient funding for system development or maintenance. Mitigation: Proper budget planning, cost monitoring, and approval checkpoints. | identified | 6 | 9 | 54
| R4 | Requirement Risk | Business Analyst / Client / Stakeholders | Incomplete or unclear system requirements leading to wrong features being developed. Mitigation: Requirement documentation, stakeholder meetings, and requirement validation. | identified | 5 | 9 | 45
| R6 | Business Risk | System Administrator / Management | User resistance or lack of training for staff using the system. Mitigation: Provide user training, manuals, and support sessions. | identified | 7 | 6 | 42
| R3 | Project Risk | Project Manager | Project delays due to poor scheduling or resource shortage. Mitigation: Use project management tools, clear milestones, and proper resource allocation. | identified | 7 | 5 | 35
| R2 | Technical Risk | System Developer / IT Team | System crash or database failure during result processing. Mitigation: Use reliable database systems, backup servers, and regular automated backups. | identified | 4 | 8 | 32

## Sheet2
RISK MATRIX
Impact/Probability | 1(very low) | 2(low) | 3(medium) | 4(high) | 5(very high)
5(Critical) |  |  | R4,R1
4(Major) |  |  |  | R5
3(Moderate) |  |  |  | R3,R6
2(Minor) |  |  |  | R2
1(Negligible)